# OpenNebula + Ceph + Kubernetes

Enterprise Private Cloud Architecture
For BlueHarvest AI Cloud Services
Supporting VMs, LLM Models, and Containers

Prepared for: BlueHarvest AI /
Document Version: 1.0
Date: February 10, 2026
Author: Cloud Infrastructure Team

# Table of Contents

1. Executive Summary

1.1 Overview

1.2 Key Findings

1.3 Recommendations

2. Technology Stack Overview

2.1 OpenNebula Platform

2.2 Ceph Storage

2.3 Managed Kubernetes

2.4 Integration Architecture

3. OpenNebula vs OpenStack Comparison

3.1 Feature Comparison

3.2 Complexity Analysis

3.3 Use Case Fit

4. Reference Architecture Design

4.1 Design Principles

4.2 Node Specifications and Count

4.3 Network Architecture

4.4 Storage Architecture (Ceph)

4.5 Kubernetes Integration

4.6 High Availability Design

5. Hardware and Resource Planning

5.1 Compute Nodes

5.2 Storage Nodes

5.3 Network Infrastructure

5.4 Management Nodes

6. Compliance Framework Mapping

6.1 ISO 27001:2022 Controls

6.2 SOC 2 Type II Controls

6.3 GDPR Requirements

6.4 Nigerian NDPR Compliance

6.5 Implementation Checklist

7. Cost Analysis

7.1 OpenNebula TCO Breakdown

7.2 OpenStack TCO Breakdown

7.3 Cost Comparison Matrix

7.4 5-Year ROI Analysis

7.5 Cost Optimization Strategies

8. Migration Strategy

8.1 Migration from VMware vSphere

8.2 Migration from Hyper-V

8.3 Migration from KVM/Legacy

8.4 Migration Tools and Automation

8.5 Phased Migration Approach

9. LLM and AI Workload Support

9.1 GPU Node Configuration

9.2 Model Serving Infrastructure

9.3 Container Orchestration for AI

9.4 Resource Scheduling

10. Implementation Roadmap

10.1 Phase 1: Foundation (Months 1-2)

10.2 Phase 2: Production Deployment (Months 3-4)

10.3 Phase 3: Migration (Months 5-6)

10.4 Phase 4: Optimization (Months 7-12)

11. Operational Considerations

11.1 Day 1 Operations

11.2 Day 2 Operations

11.3 Monitoring and Alerting

11.4 Backup and Disaster Recovery

12. Risk Analysis and Mitigation

12.1 Technical Risks

12.2 Business Risks

12.3 Mitigation Strategies

13. Recommendations for BlueHarvest AI

13.1 Strategic Recommendation

13.2 Implementation Priorities

13.3 Success Criteria

Appendix A: Detailed Cost Calculations

Appendix B: Compliance Checklist

Appendix C: Migration Scripts and Tools

Appendix D: Reference Links and Resources

# 1. Executive Summary

## 1.1 Overview

Purpose:
This document evaluates OpenNebula + Ceph + Managed Kubernetes as an alternative infrastructure platform for BlueHarvest AI's private cloud services. The analysis covers architecture design, compliance requirements, cost comparison with OpenStack, and migration strategies from legacy hypervisors.

Business Context:
BlueHarvest AI currently operates an OpenStack Kolla-Ansible deployment on a 64GB VPS (SSDNodes) serving Nigerian SMEs. The organization requires a cloud platform that can efficiently support:

- Traditional virtual machines (VMs) for customer workloads

- Large Language Model (LLM) hosting and inference

- Container orchestration for modern applications

- Compliance with international and Nigerian regulations

- Cost-effective scaling for growing customer base

## 1.2 Key Findings

| Category | OpenNebula + Ceph + K8s | Current OpenStack |
| --- | --- | --- |
| Complexity | Lower - simpler architecture | Higher - many services |
| Learning Curve | Moderate - easier to learn | Steep - complex components |
| Resource Overhead | 15-20% overhead | 25-30% overhead |
| Management Effort | 1-2 FTE | 2-3 FTE |
| Time to Production | 4-6 weeks | 8-12 weeks |
| Cost (3-year TCO) | ~$95,000 | ~$125,000 |
| K8s Integration | Native, streamlined | Add-on (Magnum, Kubeadm) |

## 1.3 Recommendations

Primary Recommendation: Hybrid Approach

For BlueHarvest AI's specific use case, we recommend:

- Keep OpenStack for mature VM workloads (already deployed)

- Deploy OpenNebula + Ceph + K8s for new services:

- • LLM model hosting and inference

- • Container-based customer applications

- • AI/ML development environments

- Gradual migration of suitable workloads from OpenStack to OpenNebula

- Target: 60% OpenNebula / 40% OpenStack by Year 2

Rationale:

| Factor | Justification |
| --- | --- |
| Risk Mitigation | Avoid big-bang replacement; maintain service continuity |
| Cost Optimization | 24% TCO reduction over 3 years for new workloads |
| Technical Fit | OpenNebula superior for K8s and AI/ML workloads |
| Skill Development | Team learns OpenNebula while maintaining OpenStack expertise |

# 2. Technology Stack Overview

## 2.1 OpenNebula Platform

What is OpenNebula?
OpenNebula is an open-source cloud computing platform for managing heterogeneous distributed data center infrastructures. Originally developed by the European research community, it focuses on simplicity and ease of use while maintaining enterprise-grade features.

Key Characteristics:

- Lightweight: Minimal services compared to OpenStack

- Flexible: Supports KVM, LXC, Firecracker, vCenter (VMware)

- Integrated: Single management interface for VMs, containers, bare metal

- Open Source: Apache 2.0 license, no vendor lock-in

- Mature: 15+ years of development, production-proven

Core Components:

| Component | Function |
| --- | --- |
| oned (OpenNebula Daemon) | Core orchestration engine |
| Sunstone | Web-based GUI and API |
| oneflow | Multi-tier application orchestration |
| onegate | VM-to-OpenNebula communication |
| scheduler | Resource scheduling and placement |
| drivers | Hypervisor, storage, network abstractions |

## 2.2 Ceph Storage

Why Ceph?
Ceph is a unified, distributed storage system designed for excellent performance, reliability, and scalability. It provides block, object, and file storage in a single platform.

Ceph Services:

| Service | Use Case |
| --- | --- |
| RBD (RADOS Block Device) | VM disk images, K8s persistent volumes |
| CephFS (File System) | Shared file storage, NFS replacement |
| RGW (RADOS Gateway) | S3/Swift compatible object storage |
| Monitors | Cluster state management, quorum |

Benefits for BlueHarvest AI:

- Self-healing: Automatic recovery from failures

- Scalable: Add nodes without downtime

- Cost-effective: Use commodity hardware

- No single point of failure: Distributed architecture

- High performance: Parallel I/O across nodes

## 2.3 Managed Kubernetes

Kubernetes Integration Options:

| Option | Pros | Cons |
| --- | --- | --- |
| OpenNebula + Rancher | Full K8s features, mature | Additional layer |
| OpenNebula + K3s | Lightweight, fast | Limited enterprise features |
| OpenNebula + vanilla K8s | Maximum flexibility | Manual setup |

Recommended: OpenNebula + Rancher RKE2

- Rancher provides unified K8s management

- RKE2 (Rancher Kubernetes Engine 2) is security-focused

- CNCF certified Kubernetes distribution

- Integrated with OpenNebula via marketplace

- Perfect for LLM model serving (KServe, Seldon)

## 2.4 Integration Architecture

How Components Work Together:

┌─────────────────────┐
                    │   Sunstone GUI      │
                    │   (Management)      │
                    └──────────┬──────────┘
                               │
                    ┌──────────▼──────────┐
                    │  OpenNebula Core    │
                    │  (Orchestration)    │
                    └──────────┬──────────┘
                               │
         ┌─────────────────────┼─────────────────────┐
         │                     │                     │
    ┌────▼─────┐         ┌────▼─────┐         ┌────▼─────┐
    │   KVM    │         │  Ceph    │         │ Rancher  │
    │   VMs    │         │ Storage  │         │ K8s      │
    └──────────┘         └──────────┘         └──────────┘
         │                     │                     │
    ┌────▼─────┐         ┌────▼─────┐         ┌────▼─────┐
    │ Customer │         │ VM Disks │         │   LLM    │
    │   VMs    │         │ Volumes  │         │  Models  │
    └──────────┘         └──────────┘         └──────────┘

Data Flow:

- Admin manages infrastructure via Sunstone GUI or CLI

- OpenNebula orchestrates VMs on KVM hypervisors

- Ceph provides persistent storage for VMs and K8s

- Rancher manages K8s clusters deployed by OpenNebula

- Applications run in VMs or containers as appropriate

# 3. OpenNebula vs OpenStack Comparison

## 3.1 Feature Comparison

| Feature | OpenNebula | OpenStack |
| --- | --- | --- |
| Architecture | Monolithic (single daemon) | Microservices (30+ components) |
| Installation | Single command, 30 min | Complex, 4-8 hours |
| Learning Curve | Moderate (2-4 weeks) | Steep (2-3 months) |
| Resource Overhead | 2-4GB RAM, 2 vCPU | 8-16GB RAM, 4+ vCPU |
| VM Management | Excellent | Excellent |
| Container Support | Via K8s integration | Via Magnum/Zun |
| Storage | Ceph, NFS, local, FC | Cinder (complex) |
| Networking | Simple overlay, VXLAN | Neutron (complex) |
| GUI | Sunstone (intuitive) | Horizon (comprehensive) |
| API | REST, XML-RPC | RESTful APIs |
| Multi-tenancy | Projects/groups | Projects/domains |
| HA Support | Built-in (active-passive) | Complex (requires HA setup) |
| Hybrid Cloud | Native (AWS, Azure) | Via federation |
| Edge Computing | OneProvision (excellent) | Limited |
| Documentation | Excellent, clear | Extensive but complex |
| Community | Smaller, focused | Large, diverse |
| Enterprise Support | OpenNebula Systems | Multiple vendors |
| License | Apache 2.0 | Apache 2.0 |
| Updates | Quarterly releases | Six-month cycles |
| Upgrade Path | Smooth, in-place | Can be disruptive |

## 3.2 Complexity Analysis

Service Count Comparison:

| Platform | Core Services | Total Components |
| --- | --- | --- |
| OpenNebula | 6 core services | ~15 total |
| OpenStack | 20+ core services | 50+ total |

## 3.3 Use Case Fit for BlueHarvest AI

| Workload | OpenNebula Fit | OpenStack Fit | Winner |
| --- | --- | --- | --- |
| Traditional VMs | 9/10 | 10/10 | OpenStack |
| LLM Model Hosting | 10/10 | 7/10 | OpenNebula |
| Container Workloads | 10/10 | 8/10 | OpenNebula |
| Edge Deployments | 10/10 | 5/10 | OpenNebula |
| Hybrid Cloud | 9/10 | 7/10 | OpenNebula |
| Multi-tenant SaaS | 8/10 | 10/10 | OpenStack |
| Ease of Management | 10/10 | 6/10 | OpenNebula |

# 4. Reference Architecture Design

## 4.1 Design Principles

- Scalability: Start small, scale horizontally

- High Availability: No single point of failure

- Performance: Optimized for AI/ML workloads

- Cost-Effective: Maximize resource utilization

- Simplicity: Minimize operational complexity

- Security: Defense in depth, compliance-ready

- Flexibility: Support VMs, containers, GPU workloads

## 4.2 Node Specifications and Count

Recommended Production Architecture (50-100 VMs):

### Management Cluster (3 nodes):

| Specification | Value |
| --- | --- |
| CPU | 8 vCPU (Intel Xeon or AMD EPYC) |
| RAM | 32GB DDR4 ECC |
| Storage | 500GB NVMe SSD (RAID 1) |
| Network | 2x 10GbE (bonded) |

Purpose: OpenNebula frontend (HA), Sunstone GUI, monitoring, LDAP/AD integration

### Compute Nodes (6-12 nodes):

| Specification | Value |
| --- | --- |
| CPU | 32+ vCPU (2x Intel Xeon Silver 4316) |
| RAM | 256GB DDR4 ECC (scalable to 512GB) |
| Storage | 2TB NVMe SSD (local cache) |
| Network | 2x 25GbE (bonded) or 1x 100GbE |

Purpose: Run customer VMs, K8s worker nodes

### GPU Compute Nodes (2-4 nodes for LLM):

| Specification | Value |
| --- | --- |
| CPU | 32 vCPU (AMD EPYC 7443) |
| RAM | 512GB DDR4 ECC |
| GPU | 4x NVIDIA A100 40GB or 8x L40S |
| Storage | 4TB NVMe SSD (model cache) |
| Network | 2x 100GbE (RDMA capable) |

Purpose: LLM model inference, training, AI/ML workloads

### Ceph Storage Nodes (5 nodes minimum):

| Specification | Value |
| --- | --- |
| CPU | 16 vCPU (sufficient for Ceph) |
| RAM | 128GB DDR4 ECC (2GB per OSD) |
| Cache/Journal | 2x 2TB NVMe SSD |
| Data Disks | 12x 8TB SATA HDD or 6x 4TB NVMe |
| Network | 2x 25GbE (dedicated Ceph network) |

Purpose: Ceph OSD nodes, monitors (3), managers (3)

Total Storage Capacity: ~480TB raw (160TB usable with 3x replication)

### Network Nodes (2 nodes for redundancy):

| Specification | Value |
| --- | --- |
| CPU | 8 vCPU |
| RAM | 16GB DDR4 ECC |
| Storage | 250GB SSD |
| Network | 2x 10GbE + 2x 1GbE |

Purpose: Virtual routers, VPN gateway, load balancers

### Total Node Count Summary:

| Node Type | Count | Purpose |
| --- | --- | --- |
| Management | 3 | OpenNebula, Rancher, Monitoring |
| Compute (Standard) | 6-12 | General purpose VMs |
| Compute (GPU) | 2-4 | LLM inference, AI/ML |
| Storage (Ceph) | 5 | Distributed storage |
| Network | 2 | Virtual routing, VPN |
| Total (Minimum) | 18 | Starter production cluster |
| Total (Recommended) | 26 | Full-featured production |

## 4.3 Network Architecture

Network Segmentation:

| Network | VLAN | Subnet | Purpose |
| --- | --- | --- | --- |
| Management | 10 | 10.0.10.0/24 | Node management, SSH, APIs |
| Ceph Public | 20 | 10.0.20.0/24 | Ceph client traffic |
| Ceph Cluster | 21 | 10.0.21.0/24 | Ceph OSD replication |
| VM Network | 100 | 192.168.100.0/22 | Customer VM traffic |
| Container Network | 110 | 10.244.0.0/16 | K8s pod network (Calico) |
| External/Public | - | 203.0.113.0/24 | Internet-facing IPs |

Network Topology Diagram:

Internet
                            │
                    ┌───────▼────────┐
                    │  Edge Router   │
                    │  (Firewall)    │
                    └───────┬────────┘
                            │
                    ┌───────▼────────┐
                    │   Core Switch  │
                    │   (10/25GbE)   │
                    └───┬────┬───┬───┘
                        │    │   │
        ┌───────────────┤    │   └─────────────────┐
        │               │    │                     │
    ┌───▼────┐     ┌───▼────┐              ┌─────▼──────┐
    │Management│     │Compute│              │  Storage   │
    │  Nodes  │     │ Nodes │              │ (Ceph)     │
    │ (HA)    │     │       │              │  Cluster   │
    └─────────┘     └───────┘              └────────────┘
        │               │                         │
    ┌───▼───────────────▼─────────────────────────▼───┐
    │          VM/Container Network (Overlay)         │
    │              VXLAN / Geneve                     │
    └─────────────────────────────────────────────────┘

### Network Design Specifications:

- Physical: Redundant 10GbE for management, 25GbE for compute

- Overlay: VXLAN with BGP EVPN for VM networks

- Container: Calico CNI with BGP for K8s networking

- Storage: Dedicated 25GbE for Ceph (separate from management)

- External: BGP peering with upstream provider

- Security: Microsegmentation via OpenNebula security groups

## 4.4 Storage Architecture (Ceph)

Ceph Cluster Design:

| Component | Configuration |
| --- | --- |
| Monitors (MON) | 3 nodes (quorum), on management nodes |
| Managers (MGR) | 3 nodes (active-standby), on management nodes |
| OSDs | 60 OSDs (12 disks x 5 nodes) |
| MDS (CephFS) | 2 nodes (active-standby), optional |
| RGW (Object) | 2 nodes (load balanced), optional |

Storage Pools:

| Pool Name | Type | Replication | Use Case |
| --- | --- | --- | --- |
| vm-images | RBD | 3x | VM disk images |
| k8s-volumes | RBD | 3x | K8s persistent volumes |
| fast-cache | RBD | 2x (NVMe) | High-performance workloads |
| llm-models | CephFS | 3x | Shared LLM model storage |

Performance Optimization:

- BlueStore: Use BlueStore backend (not FileStore)

- NVMe Cache: Journal/WAL on NVMe SSDs

- Crush Rules: Distribute data across failure domains

- PG Autoscaler: Automatic placement group sizing

- Scrubbing: Scheduled during off-peak hours

## 4.5 Kubernetes Integration

Rancher RKE2 Cluster Architecture:

| Component | Configuration |
| --- | --- |
| Control Plane | 3 nodes (on management cluster, HA) |
| Worker Nodes | 6-12 nodes (VMs on compute nodes) |
| GPU Workers | 2-4 nodes (VMs on GPU compute) |
| Storage Class | Ceph RBD via CSI driver |

LLM Model Serving Stack:

Kubernetes Cluster
    ├── Ingress Controller (Traefik/NGINX)
    ├── KServe (Model Serving)
    │   ├── Inference Service (vLLM backend)
    │   ├── GPU Scheduling (NVIDIA GPU Operator)
    │   └── Auto-scaling (HPA with custom metrics)
    ├── Model Storage (CephFS)
    │   ├── Llama 3.1 70B
    │   ├── Mistral 7B
    │   └── Custom fine-tuned models
    └── Monitoring
        ├── Prometheus (metrics)
        ├── Grafana (visualization)
        └── Loki (logs)

## 4.6 High Availability Design

| Component | HA Method | RPO/RTO |
| --- | --- | --- |
| OpenNebula | Active-Passive (Pacemaker) | RPO: 0, RTO: 5 min |
| Sunstone GUI | Load balanced (HAProxy) | RPO: 0, RTO: <1 min |
| Ceph | Distributed (CRUSH) | RPO: 0, RTO: Auto |
| Kubernetes | Multi-master (3 nodes) | RPO: 0, RTO: Auto |
| VMs | Live migration capable | RPO: 0, RTO: <30 sec |
| Network | Bonded NICs, VRRP | RPO: 0, RTO: <5 sec |
| Power | Dual PSU, UPS | N/A |

# 5. Hardware and Resource Planning

## 5.1 Bill of Materials (BOM)

| Component | Qty | Unit Cost | Total Cost | Notes |
| --- | --- | --- | --- | --- |
| Management Node | 3 | $3,500 | $10,500 | Dell R650 or equivalent |
| Compute Node | 10 | $4,500 | $45,000 | Dell R650 or equivalent |
| GPU Node | 3 | $45,000 | $135,000 | DGX-like with 4x A100 |
| Storage Node | 5 | $15,000 | $75,000 | High-density JBOD |
| Network Switches | 3 | $8,000 | $24,000 | 2x 25GbE + 1x 10GbE |
| Rack Infrastructure | 1 | $12,000 | $12,000 | Racks, PDU, cooling |
| Initial Licenses | 1 | $5,000 | $5,000 | Support subscriptions |
| TOTAL HARDWARE |  |  | $306,500 | Initial CapEx |

## 5.2 Power and Cooling Requirements

| Component | Power Draw | Cooling (BTU/hr) |
| --- | --- | --- |
| Management (3) | 1,200W | 4,100 |
| Compute (10) | 5,000W | 17,000 |
| GPU (3) | 10,500W | 35,800 |
| Storage (5) | 2,500W | 8,500 |
| Network | 600W | 2,000 |
| Total | 19,800W (~20kW) | 67,400 BTU/hr |

Data Center Requirements:

- Power: 30kW circuit (with headroom)

- Cooling: 25 tons HVAC capacity

- Space: 3-4 standard 42U racks

- Connectivity: Redundant 10Gbps internet uplinks

- Location: Lagos or Nigerian data center with N-Tier 3 certification

# 6. Compliance Framework Mapping

Overview:
This section maps OpenNebula + Ceph + Kubernetes architecture to key compliance frameworks required for BlueHarvest AI to serve Nigerian and international customers.

## 6.1 ISO 27001:2022 Controls

ISO/IEC 27001 Information Security Management

| Control Domain | Control ID | Implementation in Architecture |
| --- | --- | --- |
| Access Control | A.9.1 | OpenNebula RBAC, LDAP/AD integration, MFA support |
| Access Control | A.9.2 | Sunstone user management, SSH key-based authentication |
| Cryptography | A.10.1 | TLS 1.3 for APIs, encrypted VM disks (LUKS), Ceph encryption at rest |
| Physical Security | A.11.1 | Data center controls (access logs, biometric), rack locks |
| Operations Security | A.12.1 | Automated patching (Ansible), change management (Git) |
| Operations Security | A.12.4 | Centralized logging (ELK stack), SIEM integration |
| Communications | A.13.1 | Network segmentation (VLANs), microsegmentation (security groups) |
| Communications | A.13.2 | End-to-end encryption, VPN for admin access |
| System Acquisition | A.14.1 | Security requirements in procurement, vendor assessment |
| Supplier Relations | A.15.1 | SLA with hardware vendors, security clauses |
| Incident Management | A.16.1 | Incident response plan, alerting (PagerDuty/Opsgenie) |
| Business Continuity | A.17.1 | DR plan, backup to separate location, RTO/RPO defined |
| Compliance | A.18.1 | Regular audits, compliance dashboard, policy documentation |
| Asset Management | A.8.1 | CMDB in OpenNebula, asset tagging, inventory automation |
| Information Transfer | A.13.2 | IPSec VPN, SSH tunneling, API authentication tokens |

## 6.2 SOC 2 Type II Controls

Service Organization Control 2 - Trust Services Criteria

| Trust Service | Criteria | Implementation |
| --- | --- | --- |
| Security | CC6.1 - Logical Access | OpenNebula ACLs, groups, least privilege |
| Security | CC6.6 - Encryption | TLS everywhere, encrypted storage, VPN |
| Security | CC6.7 - Access Removal | Automated deprovisioning, audit logs |
| Availability | A1.2 - Monitoring | Prometheus/Grafana, uptime tracking, SLA monitoring |
| Availability | A1.3 - Recovery | HA architecture, automated failover, tested DR |
| Processing Integrity | PI1.1 - Data Quality | Input validation, checksums, integrity checks |
| Confidentiality | C1.1 - Encryption | Data at rest (Ceph), in transit (TLS), in use (SGX optional) |
| Confidentiality | C1.2 - Segregation | Multi-tenancy via projects, network isolation |
| Privacy | P3.2 - Data Retention | Automated deletion policies, compliance with GDPR |
| Privacy | P4.1 - Data Subject Rights | API for data export, right to erasure implementation |

## 6.3 GDPR Requirements

General Data Protection Regulation (EU)

| GDPR Article | Requirement | Technical Implementation |
| --- | --- | --- |
| Art. 5 - Principles | Data minimization | Collect only required data, automated cleanup |
| Art. 15 - Access | Right to access | API endpoint for data export, self-service portal |
| Art. 16 - Rectification | Right to rectify | User-editable profiles, audit trail |
| Art. 17 - Erasure | Right to be forgotten | Secure deletion (shred), Ceph scrubbing |
| Art. 20 - Portability | Data portability | Standard formats (JSON, CSV), API export |
| Art. 25 - Design | Privacy by design | Encryption default, minimal data collection |
| Art. 30 - Records | Processing records | Activity logs, data flow documentation |
| Art. 32 - Security | Appropriate security | Encryption, access controls, penetration testing |
| Art. 33 - Breach | Breach notification | Incident response plan, 72-hour notification |
| Art. 44 - Transfers | International transfers | Data residency controls, transfer agreements |

## 6.4 Nigerian NDPR Compliance

Nigeria Data Protection Regulation 2019

| NDPR Requirement | Implementation |
| --- | --- |
| Data Localization | Primary data stored in Nigerian data centers |
| Consent Management | Explicit consent tracking, opt-in mechanisms |
| Data Protection Officer | Designated DPO, contact information published |
| Audit Rights | NITDA audit cooperation, documentation available |
| Data Breach Notification | 72-hour notification to NITDA and subjects |
| Privacy Policy | Clear privacy policy, user-accessible |

## 6.5 Compliance Implementation Checklist

Priority 1 (Must-Have for Launch):

- ☑ Encryption at rest (Ceph encrypted pools)

- ☑ Encryption in transit (TLS 1.3 for all APIs)

- ☑ Access control (OpenNebula RBAC + LDAP/AD)

- ☑ Audit logging (centralized, tamper-proof)

- ☑ Network segmentation (VLANs, security groups)

- ☑ Backup and DR (3-2-1 rule, tested quarterly)

- ☑ Incident response plan (documented, team trained)

Priority 2 (First 6 Months):

- ☐ Security Information and Event Management (SIEM)

- ☐ Intrusion Detection System (IDS/IPS)

- ☐ Vulnerability scanning (weekly automated)

- ☐ Penetration testing (annual external audit)

- ☐ Compliance dashboard (real-time status)

- ☐ Data classification and tagging

- ☐ DLP (Data Loss Prevention) controls

Priority 3 (Continuous Improvement):

- ☐ ISO 27001 certification (external audit)

- ☐ SOC 2 Type II report (annual)

- ☐ Staff security training (quarterly)

- ☐ Compliance automation (policy as code)

- ☐ Third-party risk assessments

- ☐ Privacy impact assessments (PIAs)

# 7. Cost Analysis: OpenNebula vs OpenStack

## 7.1 Total Cost of Ownership (TCO) - 3 Year Analysis

Assumptions:

- 26-node cluster (3 mgmt, 10 compute, 3 GPU, 5 storage, 2 network, 3 spare)

- Supporting 100+ VMs, 5-10 LLM models, 50+ containers

- Nigerian data center (Lagos)

- 2 FTE for OpenNebula, 3 FTE for OpenStack

- Power: $0.20/kWh (Nigerian average)

### OpenNebula Total Cost of Ownership:

| Cost Category | Year 1 | Years 2-3 (Annual) | 3-Year Total |
| --- | --- | --- | --- |
| Hardware CapEx | $306,500 | $0 | $306,500 |
| Software Licenses | $5,000 | $5,000 | $15,000 |
| OpenNebula Support | $12,000 | $12,000 | $36,000 |
| Rancher Support | $8,000 | $8,000 | $24,000 |
| Data Center Colocation | $24,000 | $24,000 | $72,000 |
| Power (20kW) | $35,040 | $35,040 | $105,120 |
| Internet/Bandwidth | $12,000 | $12,000 | $36,000 |
| Staff (2 FTE) | $80,000 | $80,000 | $240,000 |
| Training | $10,000 | $5,000 | $20,000 |
| Maintenance | $0 | $15,000 | $30,000 |
| Monitoring Tools | $5,000 | $5,000 | $15,000 |
| Backup Storage | $8,000 | $4,000 | $16,000 |
| Total | $505,540 | $205,040 | $915,620 |

### OpenStack Total Cost of Ownership:

| Cost Category | Year 1 | Years 2-3 (Annual) | 3-Year Total |
| --- | --- | --- | --- |
| Hardware CapEx | $306,500 | $0 | $306,500 |
| Software Licenses | $0 | $0 | $0 |
| Red Hat OpenStack | $25,000 | $25,000 | $75,000 |
| Support Contracts | $15,000 | $15,000 | $45,000 |
| Data Center Colocation | $24,000 | $24,000 | $72,000 |
| Power (20kW) | $35,040 | $35,040 | $105,120 |
| Internet/Bandwidth | $12,000 | $12,000 | $36,000 |
| Staff (3 FTE) | $120,000 | $120,000 | $360,000 |
| Training | $20,000 | $10,000 | $40,000 |
| Maintenance | $0 | $15,000 | $30,000 |
| Monitoring Tools | $8,000 | $8,000 | $24,000 |
| Backup Storage | $8,000 | $4,000 | $16,000 |
| Total | $573,540 | $268,040 | $1,109,620 |

## 7.2 Cost Comparison Summary

| Metric | OpenNebula | OpenStack |
| --- | --- | --- |
| 3-Year TCO | $915,620 | $1,109,620 |
| Cost Difference | Baseline | +$194,000 (21% higher) |
| Annual OpEx (Y2-Y3) | $205,040 | $268,040 |
| Cost per VM (100 VMs) | $9,156 | $11,096 |

✅ OpenNebula saves $194,000 over 3 years (21% cost reduction)

## 7.3 Cost Breakdown by Category

Key Cost Drivers:

| Category | % of Total (OpenNebula) | % of Total (OpenStack) |
| --- | --- | --- |
| Hardware (CapEx) | 33% | 28% |
| Staff (OpEx) | 26% | 32% |
| Power | 11% | 9% |
| Support/Licenses | 8% | 11% |
| Data Center | 8% | 6% |
| Other | 14% | 14% |

Key Insights:

- Staffing is the largest OpEx difference: 2 FTE vs 3 FTE

- OpenStack requires more complex support (Red Hat subscription)

- OpenNebula training costs 50% less (simpler architecture)

- Hardware costs identical (same infrastructure)

- Power costs same (same hardware footprint)

## 7.4 Cost Optimization Strategies

- Phase hardware purchases (start with 18 nodes, add 8 nodes in Year 2)

- Use spot/preemptible instances for dev/test workloads

- Implement auto-scaling to reduce idle resources

- Negotiate volume discounts with hardware vendors

- Consider colocation vs on-premises (Lagos data center cheaper)

- Implement chargeback to customer projects

- Right-size VMs using monitoring data (save 15-20%)

- Use Ceph erasure coding for less critical data (2x storage efficiency)

## 7.5 Break-Even Analysis

If migrating from OpenStack to OpenNebula:

| Metric | Value |
| --- | --- |
| Annual savings | $63,000 |
| Migration cost (one-time) | $50,000 |
| Break-even period | 9.5 months |
| 3-year ROI | 288% |

# 8. Migration Strategy from VMware and Legacy Hypervisors

## 8.1 Migration Overview

Migration Principles:

- Risk Mitigation: Phased approach, no big-bang cutover

- Zero Downtime: Live migration where possible

- Validation: Test every workload before cutover

- Rollback Plan: Ability to revert at each phase

- Documentation: Detailed runbooks for each application

- Stakeholder Communication: Regular updates, clear timelines

## 8.2 Migration from VMware vSphere/ESXi

Challenge: VMware vSphere is a mature, feature-rich platform. Migration requires careful planning to preserve VM state, networking, and storage configurations.

Migration Tools:

| Tool | Method | Use Case |
| --- | --- | --- |
| OpenNebula vCenter Driver | Online (via API) | Keep vCenter, add OpenNebula orchestration |
| virt-v2v | Offline (VMDK→QCOW2) | Permanent migration to KVM |
| Veeam + OpenNebula | Backup restore | Use existing backups |
| Storage vMotion | Live storage migration | Move data to Ceph |
| Custom scripts | OVA export/import | Manual migration |

### Migration Path A: Hybrid Management (Recommended)

Keep VMware vCenter, add OpenNebula on top:

Step 1: Install OpenNebula
----------------------------------------
# Install OpenNebula on management nodes
# Install vCenter driver
sudo apt install opennebula-vcenter

# Configure vCenter integration
cat > /var/lib/one/remotes/vcenter.conf << EOF
:vcenter_host: vcenter.blueharvestai.local
:vcenter_user: opennebula@vsphere.local
:vcenter_password: <password>
:vcenter_datacenter: Production
EOF

Step 2: Import VMs from vCenter
----------------------------------------
# Import existing VMs (no migration needed!)
onevcenter import   --vcenter vcenter.blueharvestai.local   --vuser opennebula@vsphere.local   --vpass <password>

# VMs remain on vCenter, managed by OpenNebula
# No downtime, gradual adoption

Step 3: Deploy New Workloads on KVM
----------------------------------------
# New VMs deployed on OpenNebula KVM hosts
# Existing VMware VMs stay where they are
# Migrate selectively over time

Step 4: Gradual Migration
----------------------------------------
# Use virt-v2v to migrate VMs from VMware to KVM
for VM in $(onevm list --vcenter | grep Running); do
    # Export from vCenter
    govc export.ovf -vm=$VM /tmp/vm_export/
    
    # Convert to QCOW2
    qemu-img convert -f vmdk -O qcow2 \
        /tmp/vm_export/$VM.vmdk \
        /var/lib/one/datastores/100/$VM.qcow2
    
    # Import to OpenNebula KVM
    oneimage create --name $VM --datastore default \
        --path /var/lib/one/datastores/100/$VM.qcow2
done

✅ Benefits:

- Zero downtime during migration

- Gradual adoption, test thoroughly

- Leverage existing VMware investment

- Single pane of glass (OpenNebula Sunstone)

### Migration Path B: Direct Migration (virt-v2v)

Direct conversion from VMware VMDK to KVM QCOW2:

# Install virt-v2v on migration server
sudo apt install virt-v2v libguestfs-tools

# Method 1: Convert running VM (requires vCenter access)
virt-v2v -ic vpx://vcenter.blueharvestai.local/Production/cluster/esxi01?no_verify=1 \
  -o local -os /var/lib/one/datastores/100 \
  -of qcow2 \
  -bridge br0 \
  VM_NAME

# Method 2: Convert OVA export
virt-v2v -i ova VM_NAME.ova \
  -o local -os /var/lib/one/datastores/100 \
  -of qcow2

# Method 3: Batch migration script
#!/bin/bash
for VM in $(cat vmware_vms.txt); do
    echo "Migrating $VM..."
    
    # Export from vCenter
    govc export.ovf -vm=$VM /tmp/$VM/
    
    # Convert with virt-v2v
    virt-v2v -i ova /tmp/$VM/$VM.ova \
        -o local -os /var/lib/one/datastores/100 \
        -of qcow2 \
        --machine-readable
    
    # Import to OpenNebula
    oneimage create --name $VM \
        --datastore default \
        --path /var/lib/one/datastores/100/$VM-sda \
        --type OS
    
    # Create template
    onetemplate create --name $VM-template \
        --cpu 2 --memory 4096 \
        --disk $VM --network private
    
    echo "$VM migration complete"
done

### VMware to OpenNebula Mapping:

| VMware Concept | OpenNebula Equivalent | Notes |
| --- | --- | --- |
| vCenter | OpenNebula Frontend | Central management |
| ESXi Host | KVM Hypervisor | Compute node |
| Datastore | Ceph RBD Pool | Shared storage |
| vSwitch | Open vSwitch | Virtual networking |
| Port Group | Virtual Network | Network segment |
| Resource Pool | Cluster | Resource grouping |
| vMotion | Live Migration | Move running VMs |
| DRS | Scheduler | Automatic placement |

## 8.3 Migration from Microsoft Hyper-V

Hyper-V to OpenNebula Migration:

# Step 1: Export Hyper-V VM
# On Hyper-V host (PowerShell as Administrator)
Export-VM -Name "WebServer01" -Path "E:\Exports"

# Or export individual VHDX
Export-VMSnapshot -VM "WebServer01" \
    -Path "E:\Exports\WebServer01.vhdx"

# Step 2: Transfer to Linux migration server
# Use WinSCP, rsync, or scp

# Step 3: Convert VHDX to QCOW2
qemu-img convert -f vhdx -O qcow2 \
    WebServer01.vhdx \
    WebServer01.qcow2

# Or use virt-v2v for full conversion
virt-v2v -i disk WebServer01.vhdx \
    -o local -os /var/lib/one/datastores/100 \
    -of qcow2

# Step 4: Import to OpenNebula
oneimage create --name "WebServer01" \
    --datastore default \
    --path /var/lib/one/datastores/100/WebServer01.qcow2 \
    --type OS \
    --persistent

# Step 5: Create VM template
onetemplate create --name "WebServer01-template" \
    --cpu 4 --memory 8192 \
    --disk WebServer01 \
    --network private \
    --vnc

## 8.4 Migration from KVM/Legacy Hypervisors

Migrating from standalone KVM or other hypervisors:

# Scenario A: From standalone KVM to OpenNebula KVM
# VMs already in QCOW2 format

# Step 1: Stop VM on source
virsh shutdown VM_NAME

# Step 2: Copy disk image to OpenNebula datastore
scp /var/lib/libvirt/images/VM_NAME.qcow2 \
    opennebula-node:/var/lib/one/datastores/100/

# Step 3: Import to OpenNebula
oneimage create --name VM_NAME \
    --datastore default \
    --path /var/lib/one/datastores/100/VM_NAME.qcow2

# Step 4: Get VM specs from source
virsh dumpxml VM_NAME > VM_NAME.xml

# Step 5: Create matching template in OpenNebula
# Extract CPU, memory, network from XML
onetemplate create --name VM_NAME \
    --cpu $(grep -oP '<vcpu>\K[0-9]+' VM_NAME.xml) \
    --memory $(grep -oP '<memory unit=\'KiB\'>\K[0-9]+' VM_NAME.xml | awk '{print $1/1024}') \
    --disk VM_NAME

# Scenario B: From Xen to OpenNebula
# Convert Xen disk format to QCOW2 first
qemu-img convert -f raw -O qcow2 xen-disk.img opennebula-disk.qcow2

# Then follow KVM import process above

## 8.5 Phased Migration Approach (Recommended)

6-Month Migration Timeline:

| Phase | Duration | Activities | Success Criteria |
| --- | --- | --- | --- |
| Phase 0: Assessment | 2 weeks | Inventory VMs, dependencies, network Risk assessment, migration plan | Complete VM inventory Migration runbooks |
| Phase 1: Pilot | 3 weeks | Migrate 5 non-critical VMs Test all functions Rollback if needed | 5 VMs running 0 data loss Performance baseline |
| Phase 2: Dev/Test | 4 weeks | Migrate development workloads 20-30 VMs Validate with dev team | Dev team sign-off CI/CD working <5% performance variance |
| Phase 3: Staging | 4 weeks | Migrate staging environment Load testing Disaster recovery test | All tests passed DR validated Monitoring operational |
| Phase 4: Production | 8 weeks | Migrate production VMs 10-20 VMs per week Monitor closely | 100% VMs migrated SLA maintained 0 critical incidents |
| Phase 5: Optimization | 4 weeks | Tune performance Optimize costs Decommission old platform | 20% cost reduction Performance improved Old platform retired |

## 8.6 Migration Automation Scripts

Complete Migration Automation Script:

#!/bin/bash
# vmware-to-opennebula-migration.sh
# Automates migration from VMware to OpenNebula

set -e

# Configuration
VCENTER_HOST="vcenter.blueharvestai.local"
VCENTER_USER="administrator@vsphere.local"
OPENNEBULA_HOST="opennebula.blueharvestai.com"
DATASTORE_ID="100"
TEMP_DIR="/tmp/vm_migration"

# Function: Export VM from vCenter
export_vm_from_vcenter() {
    local vm_name=$1
    echo "Exporting $vm_name from vCenter..."
    
    govc export.ovf \
        -vm=$vm_name \
        $TEMP_DIR/$vm_name/
    
    echo "Export complete: $TEMP_DIR/$vm_name/"
}

# Function: Convert VMDK to QCOW2
convert_to_qcow2() {
    local vm_name=$1
    echo "Converting $vm_name to QCOW2..."
    
    qemu-img convert \
        -f vmdk \
        -O qcow2 \
        $TEMP_DIR/$vm_name/${vm_name}-disk-0.vmdk \
        $TEMP_DIR/$vm_name/${vm_name}.qcow2
    
    # Verify conversion
    qemu-img info $TEMP_DIR/$vm_name/${vm_name}.qcow2
}

# Function: Upload to OpenNebula
upload_to_opennebula() {
    local vm_name=$1
    echo "Uploading $vm_name to OpenNebula..."
    
    # Create image in OpenNebula
    IMAGE_ID=$(oneimage create \
        --name "$vm_name" \
        --datastore $DATASTORE_ID \
        --path $TEMP_DIR/$vm_name/${vm_name}.qcow2 \
        --type OS \
        --persistent \
        -f json | jq -r '.IMAGE.ID')
    
    echo "Image created: ID $IMAGE_ID"
    
    # Wait for image to be ready
    while [ "$(oneimage show $IMAGE_ID -j | jq -r '.IMAGE.STATE')" != "1" ]; do
        echo "Waiting for image to be ready..."
        sleep 5
    done
}

# Function: Create VM template
create_template() {
    local vm_name=$1
    local cpu=$2
    local memory=$3
    
    echo "Creating template for $vm_name..."
    
    cat > /tmp/${vm_name}_template.txt << EOF
NAME = "${vm_name}-template"
CPU = "$cpu"
MEMORY = "$memory"
DISK = [
    IMAGE_ID = "$IMAGE_ID"
]
NIC = [
    NETWORK = "private"
]
GRAPHICS = [
    TYPE = "vnc",
    LISTEN = "0.0.0.0"
]
EOF
    
    onetemplate create /tmp/${vm_name}_template.txt
    echo "Template created successfully"
}

# Function: Validate migration
validate_migration() {
    local vm_name=$1
    echo "Validating migration of $vm_name..."
    
    # Check image exists
    oneimage list | grep -q "$vm_name" || {
        echo "ERROR: Image not found"
        return 1
    }
    
    # Check template exists
    onetemplate list | grep -q "$vm_name" || {
        echo "ERROR: Template not found"
        return 1
    }
    
    echo "✓ Migration validated successfully"
}

# Main migration function
migrate_vm() {
    local vm_name=$1
    local cpu=${2:-2}
    local memory=${3:-4096}
    
    echo "==================================="
    echo "Starting migration of $vm_name"
    echo "==================================="
    
    mkdir -p $TEMP_DIR/$vm_name
    
    export_vm_from_vcenter "$vm_name"
    convert_to_qcow2 "$vm_name"
    upload_to_opennebula "$vm_name"
    create_template "$vm_name" "$cpu" "$memory"
    validate_migration "$vm_name"
    
    # Cleanup
    rm -rf $TEMP_DIR/$vm_name
    
    echo "==================================="
    echo "Migration of $vm_name complete!"
    echo "==================================="
}

# Usage
if [ $# -eq 0 ]; then
    echo "Usage: $0 <vm_name> [cpu] [memory_mb]"
    echo "Example: $0 WebServer01 4 8192"
    exit 1
fi

migrate_vm "$@"

## 8.7 Post-Migration Validation Checklist

- ☑ VM boots successfully in OpenNebula

- ☑ Network connectivity restored (IP addressing)

- ☑ Storage performance meets baseline

- ☑ Application functionality verified

- ☑ Monitoring and alerting configured

- ☑ Backup schedules created

- ☑ Documentation updated

- ☑ Runbook created for application

- ☑ Stakeholders notified of successful migration

- ☑ Old VM decommissioned (after 30-day hold)

## 8.8 Common Migration Challenges and Solutions

| Challenge | Impact | Solution |
| --- | --- | --- |
| Driver compatibility | VM won't boot | Install VirtIO drivers before migration |
| IP address changes | Network connectivity lost | Use DHCP or cloud-init to reconfigure |
| Performance degradation | Slower than VMware | Optimize VM placement, use SSD cache |
| Large disk images | Long transfer times | Use bandwidth throttling, migrate off-peak |
| Application dependencies | App breaks post-migration | Map all dependencies, test thoroughly |
| License activation | Software won't activate | Coordinate with vendors, re-activate |

# 9. LLM and AI Workload Support

## 9.1 GPU Node Configuration for LLM Inference

GPU Hardware Selection:

| GPU Model | VRAM | Best For | Cost/GPU | Recommendation |
| --- | --- | --- | --- | --- |
| NVIDIA A100 | 40GB/80GB | Large models (70B+) | $15,000 | Enterprise |
| NVIDIA L40S | 48GB | Balanced inference/training | $8,000 | Recommended |
| NVIDIA A10 | 24GB | Small-medium models | $4,500 | Budget |
| NVIDIA H100 | 80GB | Cutting edge, expensive | $30,000 | Future |

Recommended GPU Node Specification:

| Component | Specification |
| --- | --- |
| Server | Supermicro SYS-420GP-TNAR or Dell PowerEdge XE9680 |
| CPU | 2x AMD EPYC 9754 (128 cores total) |
| RAM | 1TB DDR5 ECC (32GB per GPU minimum) |
| GPU | 8x NVIDIA L40S (48GB each) |
| Storage | 8TB NVMe (4x 2TB RAID 0 for model cache) |
| Network | 2x 100GbE (RDMA/RoCE capable) |
| Power | 4x 3000W PSU (redundant) |
| Cooling | Liquid cooling recommended |

## 9.2 Model Serving Infrastructure

LLM Model Serving Stack:

# Architecture for serving LLMs at scale

┌─────────────────────────────────────────────┐
│           Load Balancer (Traefik)           │
│  - SSL Termination                          │
│  - Rate limiting                            │
│  - Authentication                           │
└──────────────┬──────────────────────────────┘
               │
    ┌──────────┴──────────┐
    │                     │
┌───▼────┐           ┌───▼────┐
│ vLLM   │           │ vLLM   │
│ Pod 1  │           │ Pod 2  │
│ (GPU)  │           │ (GPU)  │
└───┬────┘           └───┬────┘
    │                     │
    └──────────┬──────────┘
               │
    ┌──────────▼──────────┐
    │   Model Storage     │
    │   (CephFS)          │
    │  - Llama 3.1 70B    │
    │  - Mistral 7B       │
    │  - CodeLlama 34B    │
    └─────────────────────┘

Kubernetes Deployment for vLLM:

# vllm-deployment.yaml
apiVersion: apps/v1
kind: Deployment
metadata:
  name: vllm-llama-70b
  namespace: llm-serving
spec:
  replicas: 2
  selector:
    matchLabels:
      app: vllm-llama-70b
  template:
    metadata:
      labels:
        app: vllm-llama-70b
    spec:
      nodeSelector:
        nvidia.com/gpu: "true"
      containers:
      - name: vllm
        image: vllm/vllm-openai:latest
        command:
        - python3
        - -m
        - vllm.entrypoints.openai.api_server
        - --model
        - /models/llama-3.1-70b
        - --tensor-parallel-size
        - "4"
        - --gpu-memory-utilization
        - "0.95"
        env:
        - name: CUDA_VISIBLE_DEVICES
          value: "0,1,2,3"
        resources:
          limits:
            nvidia.com/gpu: 4
          requests:
            memory: "256Gi"
            cpu: "32"
        volumeMounts:
        - name: model-storage
          mountPath: /models
          readOnly: true
        ports:
        - containerPort: 8000
          name: http
      volumes:
      - name: model-storage
        persistentVolumeClaim:
          claimName: llm-models-pvc
---
apiVersion: v1
kind: Service
metadata:
  name: vllm-llama-70b
  namespace: llm-serving
spec:
  selector:
    app: vllm-llama-70b
  ports:
  - port: 8000
    targetPort: 8000
  type: ClusterIP
---
apiVersion: autoscaling/v2
kind: HorizontalPodAutoscaler
metadata:
  name: vllm-llama-70b-hpa
  namespace: llm-serving
spec:
  scaleTargetRef:
    apiVersion: apps/v1
    kind: Deployment
    name: vllm-llama-70b
  minReplicas: 2
  maxReplicas: 8
  metrics:
  - type: Resource
    resource:
      name: cpu
      target:
        type: Utilization
        averageUtilization: 70
  - type: Pods
    pods:
      metric:
        name: vllm_queue_length
      target:
        type: AverageValue
        averageValue: "10"

## 9.3 Supported LLM Models and Capacity

| Model | Size | GPU Requirement | Throughput | Use Case |
| --- | --- | --- | --- | --- |
| Llama 3.1 | 8B | 1x L40S | 50 tok/sec | General purpose |
| Llama 3.1 | 70B | 4x L40S | 30 tok/sec | Advanced reasoning |
| Mistral | 7B | 1x L40S | 60 tok/sec | Fast inference |
| CodeLlama | 34B | 2x L40S | 40 tok/sec | Code generation |
| Falcon | 40B | 2x L40S | 35 tok/sec | Research |
| GPT-J | 6B | 1x L40S | 70 tok/sec | Budget option |
| Custom Fine-tuned | Varies | Varies | Varies | Specialized |

Capacity Planning:

- With 3 GPU nodes (24 GPUs total): Support 6-8 concurrent large models

- With 4 GPU nodes (32 GPUs total): Support 10-12 concurrent models

- Reserve 20% capacity for bursts and failover

- Plan for 2x growth in Year 2

## 9.4 Resource Scheduling and Optimization

GPU Scheduling Strategies:

| Strategy | Use Case | Implementation |
| --- | --- | --- |
| Time-slicing | Multiple small models | NVIDIA Time-Slicing Plugin |
| MIG (Multi-Instance) | A100 partitioning | NVIDIA MIG Manager |
| Gang scheduling | Multi-GPU models | Kubernetes scheduler |
| Preemption | Priority workloads | Priority classes |

Optimization Techniques:

- Quantization: Use 4-bit/8-bit quantization (GPTQ, AWQ) to reduce memory

- Batching: Dynamic batching in vLLM for higher throughput

- Caching: KV cache optimization for repeated prompts

- Model Compilation: Use TensorRT-LLM for NVIDIA optimization

- Flash Attention: Enable for 2x speed improvement

## 9.5 AI/ML Training Infrastructure

Training vs Inference Requirements:

| Aspect | Training | Inference |
| --- | --- | --- |
| Workload Pattern | Batch, long-running | Online, low latency |
| GPU Utilization | 80-95% | 40-70% |
| Memory | Very high (80GB+) | Medium (24-48GB) |
| Network | High bandwidth (NVLink) | Moderate |
| Priority | Can wait | Must be fast |

Training Stack (Optional):

# Kubeflow for ML Training on Kubernetes
kubectl apply -k "github.com/kubeflow/manifests/example?ref=v1.8.0"

# PyTorch Training Operator
kubectl apply -f https://raw.githubusercontent.com/kubeflow/training-operator/master/manifests/overlays/standalone/kustomization.yaml

# Example PyTorchJob for fine-tuning
apiVersion: kubeflow.org/v1
kind: PyTorchJob
metadata:
  name: llama-finetuning
spec:
  pytorchReplicaSpecs:
    Master:
      replicas: 1
      template:
        spec:
          containers:
          - name: pytorch
            image: pytorch/pytorch:2.1.0-cuda12.1-cudnn8-devel
            command:
            - python
            - train.py
            resources:
              limits:
                nvidia.com/gpu: 8
    Worker:
      replicas: 3
      template:
        spec:
          containers:
          - name: pytorch
            image: pytorch/pytorch:2.1.0-cuda12.1-cudnn8-devel
            command:
            - python
            - train.py
            resources:
              limits:
                nvidia.com/gpu: 8

# 10. Implementation Roadmap

## 10.1 Phase 1: Foundation (Months 1-2)

Objectives: Build base infrastructure, install OpenNebula, configure Ceph

| Week | Task | Owner | Deliverable |
| --- | --- | --- | --- |
| 1 | Hardware procurement and delivery | Procurement | Hardware on-site |
| 1 | Network design and cabling | Network Team | Physical network ready |
| 2 | Server racking and power | DC Team | Servers powered |
| 2 | Base OS installation (Ubuntu 22.04) | SysAdmin | All nodes with OS |
| 3 | OpenNebula installation (frontend) | Cloud Team | OpenNebula operational |
| 3 | KVM hypervisor setup | Cloud Team | Compute nodes ready |
| 4 | Ceph cluster deployment | Storage Team | Ceph operational |
| 4-5 | Network configuration (VLANs, overlays) | Network Team | Network segmentation |
| 5-6 | Monitoring setup (Prometheus, Grafana) | Ops Team | Monitoring dashboard |
| 6-8 | Testing and validation | All Teams | Test report, sign-off |

## 10.2 Phase 2: Kubernetes and LLM (Months 3-4)

Objectives: Deploy Kubernetes, configure GPU nodes, deploy first LLM

| Week | Task | Owner | Deliverable |
| --- | --- | --- | --- |
| 9 | Rancher RKE2 installation | Cloud Team | K8s cluster operational |
| 9 | GPU node configuration | GPU Team | GPU operators installed |
| 10 | Ceph CSI driver setup | Storage Team | PVC creation working |
| 10 | Network policies and Calico | Network Team | Container networking |
| 11 | vLLM deployment | AI Team | First model serving |
| 11-12 | Model storage setup (CephFS) | Storage Team | Model repository |
| 12 | API gateway and authentication | Dev Team | Secure API access |
| 13-16 | Load testing and optimization | All Teams | Performance baseline |

## 10.3 Phase 3: Migration (Months 5-6)

Objectives: Migrate workloads from existing platforms

- Week 17-18: Pilot migration (5 non-critical VMs)

- Week 19-20: Dev/Test environment migration

- Week 21-22: Staging environment migration

- Week 23-24: Production migration (first wave)

- Week 25-26: Production migration (final wave)

## 10.4 Phase 4: Optimization and Scale (Months 7-12)

- Performance tuning and optimization

- Cost optimization (chargeback implementation)

- Compliance certification preparation

- Capacity planning for next 12 months

- Staff training and documentation

- Customer onboarding and migration

### Implementation Success Criteria:

| Metric | Target |
| --- | --- |
| Uptime SLA | 99.9% |
| VM deployment time | <5 minutes |
| LLM inference latency | <100ms (p95) |
| Storage performance | >10,000 IOPS |
| Network throughput | >20Gbps |
| Mean Time to Recovery | <30 minutes |
| Customer satisfaction | >4.5/5.0 |

# 11. Operational Considerations

## 11.1 Day 1 Operations (Initial Deployment)

Critical Day 1 Activities:

| Activity | Status |
| --- | --- |
| DNS configuration and domain setup | ☐ |
| SSL/TLS certificates installation | ☐ |
| LDAP/Active Directory integration | ☐ |
| Initial user accounts and groups | ☐ |
| Network routing and firewall rules | ☐ |
| Backup configuration and first backup | ☐ |
| Monitoring alerts configured | ☐ |
| Runbooks and SOPs documented | ☐ |
| Incident response contacts | ☐ |
| Change management process | ☐ |

## 11.2 Day 2 Operations (Ongoing)

Daily Operations:

- Monitor dashboard for alerts (Grafana)

- Review backup success/failures

- Check Ceph cluster health

- Review security logs for anomalies

- Respond to tickets and incidents

Weekly Operations:

- Patch management (security updates)

- Capacity planning review

- Performance analysis

- Backup restoration tests (sample)

- Team sync meeting

Monthly Operations:

- Full DR test

- Security vulnerability scan

- Compliance audit check

- Cost analysis and optimization

- Customer usage reports

## 11.3 Monitoring and Alerting

Monitoring Stack:

| Component | Tool | Metrics |
| --- | --- | --- |
| Infrastructure | Prometheus + Node Exporter | CPU, RAM, disk, network |
| OpenNebula | OneGate + Sunstone API | VM count, host status, capacity |
| Ceph | Ceph Manager Dashboard | OSD status, PG health, capacity |
| Kubernetes | kube-state-metrics | Pod status, deployments, resources |
| GPU | DCGM Exporter | GPU util, memory, temperature |
| Application | Custom exporters | vLLM metrics, API latency |

Alert Rules (Critical):

# prometheus-alerts.yaml
groups:
- name: infrastructure
  rules:
  - alert: HostDown
    expr: up == 0
    for: 5m
    labels:
      severity: critical
    annotations:
      summary: "Host {{ $labels.instance }} is down"
      
  - alert: HighCPUUsage
    expr: 100 - (avg by (instance) (irate(node_cpu_seconds_total{mode="idle"}[5m])) * 100) > 90
    for: 10m
    labels:
      severity: warning
      
  - alert: HighMemoryUsage
    expr: (node_memory_MemTotal_bytes - node_memory_MemAvailable_bytes) / node_memory_MemTotal_bytes * 100 > 90
    for: 5m
    labels:
      severity: warning
      
  - alert: DiskSpaceLow
    expr: (node_filesystem_avail_bytes / node_filesystem_size_bytes) * 100 < 10
    for: 5m
    labels:
      severity: critical

- name: ceph
  rules:
  - alert: CephHealthError
    expr: ceph_health_status == 2
    for: 5m
    labels:
      severity: critical
    annotations:
      summary: "Ceph cluster health is ERROR"
      
  - alert: CephOSDDown
    expr: ceph_osd_up == 0
    for: 5m
    labels:
      severity: critical

- name: kubernetes
  rules:
  - alert: PodCrashLooping
    expr: rate(kube_pod_container_status_restarts_total[15m]) > 0
    for: 5m
    labels:
      severity: warning
      
  - alert: PodNotReady
    expr: sum by (namespace, pod) (kube_pod_status_phase{phase!="Running"}) > 0
    for: 10m
    labels:
      severity: warning

## 11.4 Backup and Disaster Recovery

Backup Strategy (3-2-1 Rule):

| Data Type | Frequency | Retention | Tool |
| --- | --- | --- | --- |
| VM disks | Daily incremental | 7 daily, 4 weekly, 12 monthly | Ceph snapshots |
| OpenNebula DB | Hourly | 24 hours | mysqldump + rsync |
| K8s etcd | Hourly | 24 hours | Velero |
| LLM models | Weekly | 3 months | rclone to object storage |

Disaster Recovery Plan:

| Scenario | RTO | Recovery Procedure |
| --- | --- | --- |
| Single node failure | 5 minutes | Automatic failover, live migration |
| Storage node failure | 0 (transparent) | Ceph self-healing, data rebalance |
| Network failure | 1 minute | Automatic failover to backup link |
| Data center outage | 4 hours | Activate DR site, restore from backups |
| Ransomware attack | 8 hours | Restore from offline backups, rebuild |

## 11.5 Change Management

Change Request Process:

- Submit change request (via ticketing system)

- Technical review by team lead

- Risk assessment and rollback plan

- Schedule change window (announce to customers)

- Execute change in maintenance window

- Validate change success

- Update documentation

- Close change request

Change Windows:

- Standard: Tuesdays 1:00-5:00 AM WAT (weekly)

- Emergency: Any time (with approval)

- Major: Quarterly (full DR test + upgrades)

# 12. Risk Analysis and Mitigation

## 12.1 Technical Risks

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| Hardware failure | Medium | High | Redundant components, spare parts inventory |
| Data loss | Low | Critical | Ceph replication, offsite backups, 3-2-1 rule |
| Performance issues | Medium | Medium | Load testing, capacity planning, monitoring |
| Security breach | Low | Critical | Defense in depth, regular audits, pentesting |
| Network outage | Low | High | Redundant links, BGP failover, 4G backup |
| Power outage | Medium | High | UPS (15 min), generator (24hr), dual PSUs |

## 12.2 Business Risks

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| Budget overrun | Medium | High | Phased procurement, cost tracking, contingency (20%) |
| Staff turnover | Medium | Medium | Documentation, cross-training, managed services |
| Vendor lock-in | Low | Medium | Open source strategy, avoid proprietary formats |
| Regulatory changes | Low | High | Compliance monitoring, flexible architecture |
| Competition | High | Medium | Differentiation (LLM focus), Nigerian market advantage |

## 12.3 Mitigation Strategies

Key Risk Mitigation Approaches:

- Technical: Redundancy at every layer, automated failover, comprehensive monitoring

- Operational: Detailed runbooks, regular DR tests, change management

- Financial: Phased investment, cost tracking, quarterly reviews

- People: Cross-training, documentation, managed services backup

- Compliance: Regular audits, automated compliance checks, legal counsel

# 13. Recommendations for BlueHarvest AI

## 13.1 Strategic Recommendation

RECOMMENDATION: Hybrid Dual-Platform Strategy

Deploy OpenNebula + Ceph + Kubernetes alongside existing OpenStack:

| Platform | Use For | Target Split (Year 2) |
| --- | --- | --- |
| OpenStack (Existing) | Traditional VMs, mature workloads, legacy apps | 40% |
| OpenNebula (New) | LLM hosting, containers, AI/ML, new services | 60% |
| Both | Edge computing, hybrid cloud, customer choice | Flexible |

Rationale:

- ✓ Minimize risk: No big-bang replacement

- ✓ Leverage investments: Keep OpenStack expertise and infrastructure

- ✓ Optimize costs: 21% TCO reduction on new workloads

- ✓ Technical fit: OpenNebula superior for K8s and LLM

- ✓ Competitive advantage: Offer both platforms to customers

- ✓ Gradual migration: Move workloads over 18-24 months

## 13.2 Implementation Priorities

Q1-Q2 2026 (Immediate):

- ☑ Finalize hardware procurement (order now, 8-12 week lead time)

- ☑ Hire or train 2 additional staff (OpenNebula + Ceph)

- ☑ Secure data center space (Lagos preferred)

- ☑ Design detailed network architecture

- ☑ Develop migration playbooks

Q3 2026 (Build Phase):

- ☐ Deploy OpenNebula foundation (3 management + 5 compute + 3 storage nodes)

- ☐ Configure Ceph storage (initial 120TB usable)

- ☐ Deploy Rancher RKE2 Kubernetes

- ☐ Pilot LLM model serving (Llama 3.1 8B)

- ☐ Migrate 10 dev/test VMs

Q4 2026 (Scale Phase):

- ☐ Add GPU nodes (2 nodes, 16 GPUs)

- ☐ Deploy production LLM services

- ☐ Onboard first 5 customers to new platform

- ☐ Implement chargeback and billing

- ☐ ISO 27001 readiness assessment

2027 (Maturity Phase):

- ☐ Scale to 60% of workloads on OpenNebula

- ☐ Add 5 compute + 2 GPU + 2 storage nodes

- ☐ SOC 2 Type II certification

- ☐ Expand to edge locations (Abuja, Port Harcourt)

- ☐ Launch AI-as-a-Service offerings

## 13.3 Success Criteria

Measure success against these KPIs:

| KPI | Target | Measurement |
| --- | --- | --- |
| Platform Uptime | 99.9% | Monthly uptime report |
| VM Provision Time | <5 minutes | Automated monitoring |
| LLM Inference Latency | <100ms (p95) | Application metrics |
| Customer Satisfaction | >4.5/5 | Quarterly surveys |
| Cost per VM | <$100/month | Chargeback reports |
| Staff Productivity | 100 VMs per FTE | Operational metrics |
| Security Incidents | 0 major | Incident reports |
| Backup Success Rate | 100% | Daily validation |
| Time to Market (new services) | <30 days | Project tracking |
| Customer Growth | 20% YoY | Sales pipeline |

## 13.4 Final Thoughts

Why This Recommendation Makes Sense:

1. Right Tool for the Job
OpenNebula excels at Kubernetes and LLM workloads—exactly what BlueHarvest AI needs for growth. OpenStack remains excellent for traditional VMs.

2. Cost Efficiency
21% lower TCO over 3 years ($194,000 savings) while maintaining capability. This includes reduced staffing (2 vs 3 FTE) and lower licensing costs.

3. Risk Management
Dual-platform approach minimizes migration risk. No forced "lift and shift" of working systems.

4. Competitive Advantage
First Nigerian cloud provider offering both traditional VMs and AI/LLM services. Data sovereignty advantage over international providers.

5. Technical Excellence
OpenNebula's simplicity means faster innovation. Team can focus on customer value, not infrastructure complexity.

Next Steps:

- Schedule workshop with technical team (architecture review)

- Obtain budget approval ($306K CapEx + $200K/year OpEx)

- Initiate hardware procurement (12-week lead time)

- Hire/train staff (2 FTE, start Q2)

- Begin detailed design phase (network, security, compliance)

# Appendix A: Detailed Cost Calculations

Hardware Cost Breakdown:

| Item | Qty | Unit Price | Total | Vendor |
| --- | --- | --- | --- | --- |
| Management Node - Dell R650 | 3 | $3,500 | $10,500 | Dell Nigeria |
| - 2x Intel Xeon Silver 4316 |  |  |  |  |
| - 32GB RAM |  |  |  |  |
| - 500GB NVMe |  |  |  |  |
| Compute Node - Dell R650 | 10 | $4,500 | $45,000 | Dell Nigeria |
| - 2x Intel Xeon Silver 4316 |  |  |  |  |
| - 256GB RAM |  |  |  |  |
| - 2TB NVMe |  |  |  |  |
| GPU Node - Supermicro SYS-420GP | 3 | $45,000 | $135,000 | Supermicro |
| - 2x AMD EPYC 9754 |  |  |  |  |
| - 512GB RAM |  |  |  |  |
| - 8x NVIDIA L40S |  |  |  |  |
| Storage Node - Supermicro 4U | 5 | $15,000 | $75,000 | Supermicro |
| - 16 vCPU |  |  |  |  |
| - 128GB RAM |  |  |  |  |
| - 12x 8TB HDD |  |  |  |  |
| Network Switch 25GbE | 2 | $8,000 | $16,000 | Cisco |
| Network Switch 10GbE | 1 | $8,000 | $8,000 | Cisco |
| Rack + PDU + Cables | 1 | $12,000 | $12,000 | APC |
| TOTAL HARDWARE |  |  | $306,500 |  |

# Appendix B: Compliance Checklist

ISO 27001:2022 Implementation Checklist (Abridged):

- ☑ A.5 - Information security policies documented

- ☑ A.6 - Organization roles and responsibilities defined

- ☑ A.7 - Human resources security procedures

- ☑ A.8 - Asset management and classification

- ☑ A.9 - Access control policies and procedures

- ☐ A.10 - Cryptographic controls (in progress)

- ☐ A.11 - Physical security controls (data center)

- ☐ A.12 - Operations security (patch management)

# Appendix C: Key Resources and References

Official Documentation:

- OpenNebula: https://docs.opennebula.io/

- Ceph: https://docs.ceph.com/en/latest/

- Rancher: https://rancher.com/docs/rke2/latest/en/

- vLLM: https://docs.vllm.ai/

Community and Support:

- OpenNebula Forum: https://forum.opennebula.io/

- Ceph Mailing Lists: https://ceph.io/en/community/

- Rancher Community: https://slack.rancher.io/

- CNCF Slack: https://cloud-native.slack.com/

Training Resources:

- OpenNebula Training: https://opennebula.io/training/

- Ceph Fundamentals: Linux Foundation Training

- Kubernetes Certification: CKA, CKAD from CNCF

- NVIDIA GPU Training: Deep Learning Institute

# Appendix D: Glossary

| Term | Definition |
| --- | --- |
| Ceph | Distributed storage system providing block, object, and file storage |
| CRUSH | Controlled Replication Under Scalable Hashing - Ceph data placement algorithm |
| KVM | Kernel-based Virtual Machine - Linux hypervisor |
| OSD | Object Storage Daemon - Ceph storage component |
| RBD | RADOS Block Device - Ceph block storage |
| vLLM | High-throughput LLM inference server |
| Sunstone | OpenNebula web-based management interface |
| RKE2 | Rancher Kubernetes Engine 2 - CNCF certified K8s distribution |
| CSI | Container Storage Interface - K8s storage standard |
| CNI | Container Network Interface - K8s network standard |
| VXLAN | Virtual Extensible LAN - network virtualization protocol |
| BGP | Border Gateway Protocol - internet routing protocol |
| RBAC | Role-Based Access Control - authorization mechanism |
| TCO | Total Cost of Ownership - lifetime cost analysis |
| SLA | Service Level Agreement - performance commitment |

# END OF DOCUMENT

Prepared for BlueHarvest AI
Document Version: 1.0
Date: February 10, 2026

For questions or clarifications, contact:
Cloud Infrastructure Team
cloud-ops@blueharvestai.com